# Defense Program Management Tool

Comprehensive Architecture Plan

January 2026 | Version 2.0

# Table of Contents

# Executive Summary

This document presents a comprehensive architecture plan for a Defense Program Management Tool designed to optimize program cost and schedule baselines for resource-constrained projects. The solution leverages probabilistic cost estimation and Schedule Risk Analysis (SRA) methods to provide program managers with data-driven decision support.

This version includes a fully integrated Schedule Manager module, eliminating external dependencies on Microsoft Project Server. This self-contained approach provides complete control over schedule data, ensures EVMS compliance at the source, and reduces integration complexity and licensing costs.

## Key Design Decisions

- Modular Monolith Architecture — enables rapid development while maintaining clean boundaries

- Built-in Schedule Manager — EVMS-compliant scheduling engine with CPM, resource leveling, and IMS support

- Python/FastAPI Backend — optimal for data science workloads with strong typing

- React/TypeScript Frontend — proven stack for complex dashboards including Gantt visualization

- PostgreSQL Primary Database — enterprise-grade reliability with excellent JSON support

- Redis for Caching & Scenarios — enables high-performance what-if analysis

# 1. High-Level Architecture

## 1.1 Architecture Pattern Selection

After careful evaluation of project constraints, I recommend a Modular Monolith architecture:

| Factor | Microservices | Traditional Monolith | Modular Monolith ✓ |
| --- | --- | --- | --- |
| Team Size (1 dev) | Poor — operational overhead | Good — simple deployment | Excellent — single deploy, clean code |
| 3-Month Timeline | Poor — infrastructure setup | Good — fast initial dev | Excellent — fast + maintainable |
| Future Scalability | Excellent — independent scaling | Poor — coupled components | Good — easy to extract later |
| Defense Compliance | Complex — distributed audit | Good — centralized logging | Excellent — centralized + clear modules |

## 1.2 System Components

Schedule Manager Module (NEW): Full-featured scheduling engine providing EVMS-compliant schedule management. Includes WBS definition, task/activity management, dependency management (FS, SS, FF, SF), CPM calculation engine, resource assignment and leveling, and IMS format support. Replaces external scheduling tool dependencies.

Integration Engine Module: Handles external communications with adapters for Jira (work package backup data) and Cobra (cost actuals). Supports import/export of standard schedule formats (MS Project XML, Primavera XER).

Probabilistic Analysis Module: Monte Carlo simulation engine, probability distribution fitting, correlation modeling, and multiple optimization algorithms (genetic algorithms, linear programming).

Baseline Management Module: Manages baselines with version control, immutable snapshots, and EVMS calculations (BCWS, BCWP, ACWP, SV, CV, SPI, CPI). Integrated with Schedule Manager for PMB tracking.

Scenario Planning Module: What-if analysis through branched scenarios that reference (but never modify) the baseline. Supports comparison, sensitivity analysis, and promotion workflows.

Reporting & Compliance Module: Generates DFARS-compliant reports, EVMS variance analysis, IPMR, and custom dashboards. Complete audit trails.

# 2. Schedule Manager Module (Deep Dive)

The Schedule Manager provides EVMS-compliant scheduling capabilities without external dependencies.

## 2.1 EVMS Compliance Requirements

Designed to satisfy EVMS guidelines per ANSI/EIA-748:

| Guideline | Requirement | Implementation |
| --- | --- | --- |
| GL 6 | Schedule work consistent with WBS/OBS | Hierarchical WBS with OBS mapping; work packages inherit constraints |
| GL 7 | Identify products and milestones | Milestone tracking with weighted milestone and % complete methods |
| GL 8 | Establish time-phased budgets (PMB) | Time-phased BCWS with CA and WP level budgets |
| GL 21 | Identify significant BCWS/BCWP differences | Automated SV/SPI with configurable thresholds and alerts |
| GL 27 | Develop EAC through revised estimates | Multiple EAC methods: mathematical, comprehensive, independent ETC |

## 2.2 Core Capabilities

### Work Breakdown Structure (WBS)

- Unlimited hierarchy depth with summary roll-up calculations

- Control Account (CA) designation at any WBS level

- Work Package (WP) definition with discrete scope boundaries

- Planning Package support for future scope not yet at WP level

- WBS Dictionary with scope, deliverables, and acceptance criteria

### Scheduling Engine

- Critical Path Method (CPM) with forward and backward pass

- Dependency types: FS, SS, FF, SF with lag/lead support

- Constraints: ASAP, ALAP, SNET, FNLT

- Multiple critical paths and near-critical analysis

- Baseline vs. current comparison with variance highlighting

### Resource Management

- Resource pool with capacity calendars

- Skill-based and role-based assignment

- Loading and leveling algorithms

- Over-allocation detection and resolution

- Cost rate tables with effective dates

### Earned Value Integration

- BCWS — auto-computed from time-phased WP budgets

- BCWP — supports 0/100, 50/50, milestone weights, % complete, LOE

- SV and SPI at all WBS levels

- TSPI for completion forecasting

## 2.3 DFARS Reporting Support

| DFARS Report | Schedule Manager Data Source |
| --- | --- |
| CPR Format 1 (WBS) | WBS hierarchy with BCWS, BCWP, ACWP, BAC, EAC at all levels |
| CPR Format 2 (OBS) | WBS to Organizational structure cross-reference |
| CPR Format 3 (Baseline) | Time-phased PMB from schedule and budget data |
| Integrated Master Schedule | Full schedule export with resources and dependencies |
| Schedule Risk Assessment | Monte Carlo probability distributions for completion dates |

## 2.4 Technical Design

Data Model: Program (top-level), WBSElement (hierarchy with ltree), Activity (schedulable unit), Dependency (relationships), Resource (with calendars), Assignment (resource-activity link), Baseline (immutable snapshots).

CPM Algorithm Implementation:

- Build DAG from activities and dependencies

- Topological sort for calculation order

- Forward pass: calculate ES and EF

- Backward pass: calculate LS and LF

- Compute Total Float (TF = LS - ES) and Free Float

- Identify critical path(s) where TF = 0

Performance target: 1000 activities calculated in under 500ms.

## 2.5 Frontend Visualization

- Interactive Gantt Chart — drag-and-drop editing, dependency lines, critical path highlighting

- WBS Tree View — collapsible hierarchy with inline editing

- Resource Histogram — stacked bar visualization of resource loading

- S-Curve Display — cumulative BCWS/BCWP/ACWP comparison

Gantt library options: DHTMLX Gantt (commercial, ~$999), Bryntum (commercial), Frappe Gantt (open-source MVP option).

# 3. Technology Stack

## 3.1 Frontend: React 18 with TypeScript

| Technology | React/TS ✓ | Vue.js 3 | Angular 17 |
| --- | --- | --- | --- |
| Gantt Libraries | Excellent — DHTMLX, Bryntum | Good — DHTMLX supports Vue | Fair — fewer options |
| Data Visualization | Excellent — D3, Recharts, Plotly | Good — Chart.js | Good — ngx-charts |
| Solo Dev Velocity | High — component reuse | High — less boilerplate | Lower — more ceremony |

Key libraries: React Query, DHTMLX/Frappe Gantt, Recharts/Plotly, AG Grid, Tailwind CSS.

## 3.2 Backend: Python 3.11+ with FastAPI

| Technology | Python/FastAPI ✓ | Node.js | C#/.NET |
| --- | --- | --- | --- |
| Monte Carlo/Stats | Excellent — NumPy, SciPy | Poor — limited | Fair — Math.NET |
| Graph Algos (CPM) | Excellent — NetworkX | Fair — limited | Good — QuickGraph |
| Optimization | Excellent — scipy, DEAP, OR-Tools | Poor | Fair — Accord.NET |

Key libraries: NetworkX, NumPy/SciPy, DEAP, PuLP/OR-Tools, SQLAlchemy 2.0, Celery, Pydantic v2.

## 3.3 Database: PostgreSQL 15+ with Redis

PostgreSQL for ACID-compliant persistent storage with ltree extension for WBS hierarchy queries. Redis for caching, session management, and scenario branching.

# 4. Data Architecture

## 4.1 Schema Approach

Hybrid approach: normalized tables for core entities with JSONB for flexible attributes.

Core Entities: Program & WBS (ltree hierarchy), Schedule (activities, dependencies, constraints), Resources (definitions, calendars, assignments), Cost (BCWS, BCWP, ACWP, time-series), Baselines (immutable snapshots with event sourcing).

## 4.2 Caching Strategy

| Data Type | Cache | TTL | Invalidation |
| --- | --- | --- | --- |
| Dashboard Aggregates | Redis | 5 min | Schedule/cost edit |
| CPM Results | Redis | Until edit | Activity/dependency change |
| Simulation Results | Redis | 1 hour | Parameter change |
| Active Scenarios | Redis | 24 hours | Manual/promotion |

# 5. Scalability & Performance

## 5.1 Capacity Planning

| Metric | Estimated | Design Capacity |
| --- | --- | --- |
| Concurrent Sessions | 100 users | 500 users (5x) |
| API Requests/Second | ~50 RPS | 250 RPS |
| CPM Recalculations/Min | ~20 | 100 (cached) |
| Concurrent Simulations | 5-10 | 50 (queued) |

## 5.2 Bottlenecks & Solutions

CPM Calculation: NetworkX O(V+E), incremental recalc, cached ES/EF/LS/LF values.

Monte Carlo: Vectorized NumPy (100x faster), Celery workers, progressive streaming.

Gantt Rendering: Virtualized rendering, hierarchical collapse, progressive loading.

# 6. Security Considerations

## 6.1 Authentication & Authorization

Authentication: OAuth 2.0/OIDC with enterprise SSO (Azure AD, Okta, SAML). Fallback: bcrypt + TOTP MFA. JWT with 15-min expiry + refresh tokens.

| Role | Permissions | Scope |
| --- | --- | --- |
| Program Manager | Full access: schedule, baselines, scenarios, reports, approvals | Program |
| Scheduler | Edit activities, dependencies, resources; create scenarios; no baseline approval | Program |
| Control Account Mgr | Edit WPs within assigned CAs, create scenarios | CA |
| Analyst | Read-only, personal scenarios, run simulations | Program |
| System Admin | User mgmt, integrations, settings, audit logs | Global |

## 6.2 Compliance

- Encryption: AES-256 at rest (PostgreSQL TDE), TLS 1.3 in transit

- Data Classification: All program data as CUI by default

- DFARS 252.204-7012 — CUI handling requirements

- NIST SP 800-171 — Controls mapped to implementation

- EVMS per ANSI/EIA-748 — Data integrity controls

# 7. Development & Deployment

## 7.1 Repository Structure

- /api — FastAPI backend with Schedule Manager

- /web — React frontend with Gantt components

- /shared — Types and utilities

- /tests — Integration tests

## 7.2 Testing Strategy

| Type | Tools | Target | Frequency |
| --- | --- | --- | --- |
| Unit | pytest, Jest | 90% CPM, 80% other | Every commit |
| Integration | pytest + TestClient | All API endpoints | Every PR |
| CPM Validation | Reference schedules | 100% accuracy | Scheduler changes |
| E2E | Playwright | Critical journeys | Pre-deploy |
| Security | Bandit, Snyk, ZAP | Zero high/critical | Daily |

## 7.3 CI/CD Pipeline (GitHub Actions)

- Lint + Type Check

- Unit Tests (parallel) + CPM validation

- Integration Tests

- Docker Build + Security Scan

- Deploy Staging (auto) → E2E Tests → Deploy Prod (manual gate)

# 8. Risks & Trade-offs

## 8.1 Key Technical Risks

- Schedule Manager Complexity

Risk: Building robust CPM, resource leveling, EVMS integration could consume most of timeline. Medium-High probability.

Mitigation: Start with core CPM (well-documented), use NetworkX, phase resource leveling post-MVP.

- Single Developer Bus Factor

Risk: One dev means illness/departure halts progress. Medium probability.

Mitigation: Comprehensive documentation, automated testing, consider part-time contractor for review.

- EVMS Scope Creep

Risk: Full 32-guideline compliance reveals hidden complexity. Medium-High probability.

Mitigation: Define minimum viable EVMS subset (GL 6-8, 21, 27), validate reports early with stakeholders.

- User Adoption Resistance

Risk: Users resist switching from MS Project. High probability (adoption explicitly a constraint).

Mitigation: Support MS Project XML import, match familiar UX, involve users in design, provide Excel export.

## 8.2 Trade-offs

| Decision | Trade-off | Rationale |
| --- | --- | --- |
| Built-in Schedule Manager | Significant dev effort, reduced feature set vs MS Project | Eliminates dependency, licensing, sync complexity; native EVMS integration |
| Modular Monolith | Delayed horizontal scaling | Dev velocity critical with 1 dev / 3 months |
| Python for Scheduling | Slower than C++ for graphs | NetworkX sufficient; NumPy/SciPy essential for Monte Carlo |

## 8.3 MVP Scope (3-Month Target)

Month 1 — Schedule Foundation: Auth, PostgreSQL schema (WBS/activity/dependency), CPM engine, basic Gantt with editing, MS Project XML import.

Month 2 — EVMS Integration: BCWS time-phasing, basic EV methods, Monte Carlo engine, scenario branching, EVMS dashboard (SPI, CPI, S-curve).

Month 3 — Compliance & Polish: EVMS/DFARS reports (CPR 1, 3, 5), Jira integration, basic resource assignment, what-if views, security hardening.

Post-MVP: Resource leveling, Cobra integration, advanced optimization, correlation modeling.

# 9. Conclusion

This architecture centers on a self-contained Schedule Manager that eliminates MS Project Server dependency while providing full EVMS/DFARS compliance.

- Complete Data Control — All schedule data internal, tight EVMS integration

- Reduced Complexity — No sync challenges, external auth, or version issues

- Lower Total Cost — No MS Project licensing; single platform

- Better UX — Seamless flow from scheduling through Monte Carlo to EVMS reporting

The trade-off is development effort, but focusing MVP on core CPM with NetworkX and phasing advanced features keeps this achievable in 3 months. Python/FastAPI, React/TypeScript, and PostgreSQL provide strong foundations for both scheduling and probabilistic analysis.