# Test-Driven Development Plan

Defense Program Management Tool

Schedule Manager & EVMS Compliance Engine

January 2026 | Version 1.0

# Table of Contents

# Introduction

This document defines the Test-Driven Development (TDD) strategy for the Defense Program Management Tool. Given the critical nature of EVMS compliance and schedule calculations, TDD is essential to ensure correctness from the start.

## TDD Philosophy for This Project

The Schedule Manager and EVMS modules are mathematically deterministic — given the same inputs, they must always produce the same outputs. This makes them ideal candidates for TDD because:

- CPM calculations have known correct answers that can be verified against reference schedules

- EVMS metrics (SPI, CPI, SV, CV) have precise mathematical definitions

- Edge cases are well-defined (circular dependencies, negative float, etc.)

- Regression prevention is critical — a bug in schedule calculation could affect contract compliance

## Testing Tools & Framework

| Layer | Tool | Purpose |
| --- | --- | --- |
| Backend Unit | pytest + pytest-cov | Python unit tests with coverage |
| Backend Integration | pytest + httpx (TestClient) | API endpoint testing |
| Frontend Unit | Jest + React Testing Library | Component and hook testing |
| E2E | Playwright | Full user journey tests |
| Mocking | pytest-mock, unittest.mock | Database, external services |
| Fixtures | pytest fixtures, Factory Boy | Test data generation |

# 1. Test Cases Overview

Test cases are organized by module and test type. Coverage targets: 90% for CPM engine, 85% for EVMS calculations, 80% for other business logic.

## 1.1 Schedule Manager — Unit Tests

WBS Module (Target: 85% coverage)

| Test Case | Input | Expected Output |
| --- | --- | --- |
| test_create_wbs_element | name, parent_id, wbs_code | WBSElement with correct hierarchy |
| test_wbs_hierarchy_depth | Nested elements 5 levels deep | Correct parent-child relationships |
| test_wbs_code_generation | Parent WBS '1.2' | Child WBS '1.2.1', '1.2.2' |
| test_control_account_designation | WBS element | is_control_account = True |
| test_wbs_budget_rollup | Children with budgets | Parent = sum of children |
| test_delete_wbs_cascades | Parent with children | All descendants deleted |

Activity Module (Target: 85% coverage)

| Test Case | Input | Expected Output |
| --- | --- | --- |
| test_create_activity | name, duration, wbs_id | Activity linked to WBS |
| test_activity_duration_validation | duration = -5 | ValidationError raised |
| test_activity_constraint_types | SNET with date | Constraint stored correctly |
| test_milestone_zero_duration | is_milestone = True | duration forced to 0 |
| test_activity_progress_update | percent_complete = 50 | Progress recorded with date |

CPM Engine (Target: 90% coverage) — CRITICAL

| Test Case | Input | Expected Output |
| --- | --- | --- |
| test_forward_pass_simple | A→B→C, each 5 days | ES: 0,5,10 / EF: 5,10,15 |
| test_backward_pass_simple | A→B→C, each 5 days | LS: 0,5,10 / LF: 5,10,15 |
| test_critical_path_identification | Network with 2 paths | Longest path marked critical |
| test_total_float_calculation | Non-critical activity | TF = LS - ES (positive) |
| test_free_float_calculation | Activity with successor | FF = min(ES_succ) - EF |
| test_fs_dependency | A FS B | B.ES = A.EF |
| test_ss_dependency | A SS B | B.ES = A.ES |
| test_ff_dependency | A FF B | B.EF = A.EF |
| test_sf_dependency | A SF B | B.EF = A.ES |
| test_lag_positive | A FS+3 B | B.ES = A.EF + 3 |
| test_lag_negative_lead | A FS-2 B | B.ES = A.EF - 2 |
| test_multiple_predecessors | A,B → C | C.ES = max(A.EF, B.EF) |
| test_snet_constraint | SNET = Day 10 | ES = max(calc, 10) |
| test_fnlt_constraint | FNLT = Day 20 | LF = min(calc, 20) |

## 1.2 EVMS Module — Unit Tests

Earned Value Calculations (Target: 90% coverage)

| Test Case | Input | Expected Output |
| --- | --- | --- |
| test_bcws_calculation | Budget $100K, 50% planned | BCWS = $50,000 |
| test_bcwp_percent_complete | Budget $100K, 30% complete | BCWP = $30,000 |
| test_bcwp_0_100_method | Not complete | BCWP = $0 |
| test_bcwp_50_50_method | Started but not done | BCWP = 50% of budget |
| test_bcwp_milestone_weights | Milestones with weights | BCWP = sum of completed |
| test_schedule_variance | BCWP=40K, BCWS=50K | SV = -$10,000 |
| test_cost_variance | BCWP=40K, ACWP=45K | CV = -$5,000 |
| test_spi_calculation | BCWP=40K, BCWS=50K | SPI = 0.80 |
| test_cpi_calculation | BCWP=40K, ACWP=50K | CPI = 0.80 |
| test_eac_mathematical | BAC=100K, CPI=0.8 | EAC = $125,000 |
| test_etc_calculation | EAC=125K, ACWP=45K | ETC = $80,000 |
| test_vac_calculation | BAC=100K, EAC=125K | VAC = -$25,000 |
| test_tcpi_calculation | BAC=100K, BCWP=40K, ACWP=45K | TCPI = 1.09 |

## 1.3 Integration Tests

API Integration Tests

| Test Case | Endpoint | Validation |
| --- | --- | --- |
| test_create_program_api | POST /api/programs | 201, program created in DB |
| test_create_activity_triggers_cpm | POST /api/activities | CPM recalculated, dates updated |
| test_add_dependency_updates_schedule | POST /api/dependencies | Successor dates shift correctly |
| test_baseline_snapshot_immutable | POST /api/baselines | Baseline cannot be modified |
| test_scenario_branch_isolation | POST /api/scenarios | Changes don't affect baseline |
| test_evms_rollup_to_program | GET /api/programs/{id}/evms | Aggregated metrics correct |
| test_cpr_report_generation | GET /api/reports/cpr/{id} | Valid CPR Format 1 data |
| test_unauthorized_access_blocked | GET /api/programs/{id} | 403 for wrong role |

Database Integration Tests

| Test Case | Validation |
| --- | --- |
| test_wbs_ltree_hierarchy_queries | Ancestor/descendant queries work correctly |
| test_cascade_delete_wbs | Deleting WBS removes activities, dependencies |
| test_transaction_rollback_on_error | Partial CPM failure rolls back all changes |
| test_concurrent_schedule_updates | Optimistic locking prevents conflicts |
| test_audit_log_on_baseline_change | All modifications logged with user/timestamp |

## 1.4 Edge Cases & Error Handling

CPM Edge Cases — CRITICAL

| Edge Case | Input | Expected Behavior |
| --- | --- | --- |
| Circular dependency | A→B→C→A | CircularDependencyError raised |
| Self-referencing dependency | A→A | ValidationError raised |
| Orphan activity (no deps) | Activity with no pred/succ | ES=0, valid schedule |
| Negative float | FNLT constraint violated | TF < 0, flagged as overdue |
| Zero duration activities | Milestones | ES = EF, valid calculation |
| Very large schedule | 1000 activities | Completes in < 500ms |
| Multiple critical paths | Two paths, same length | Both paths marked critical |
| Start-to-Finish only path | A SF B SF C | Dates calculated correctly |

EVMS Edge Cases

| Edge Case | Input | Expected Behavior |
| --- | --- | --- |
| Division by zero (SPI) | BCWS = 0 | SPI = None or Infinity flag |
| Division by zero (CPI) | ACWP = 0 | CPI = None or Infinity flag |
| Negative ACWP | Credit/refund posted | CV calculation handles gracefully |
| 100%+ complete | Rework causes >100% | BCWP capped at BAC or flagged |
| Future period with no BCWS | Planning gap | SV/SPI meaningful or N/A |

Input Validation Edge Cases

| Edge Case | Input | Expected Behavior |
| --- | --- | --- |
| Empty activity name | name = '' | ValidationError: name required |
| Negative duration | duration = -5 | ValidationError: must be >= 0 |
| Invalid dependency type | type = 'XX' | ValidationError: invalid type |
| Duplicate WBS code | Existing code '1.2.3' | IntegrityError: unique constraint |
| Non-existent predecessor | predecessor_id = 99999 | ForeignKeyError |
| SQL injection attempt | name = "'; DROP TABLE--" | Safely escaped, no injection |

# 2. Implementation Order

TDD implementation follows a bottom-up, simplest-first approach. Each layer builds on tested foundations.

## 2.1 Phase 1: Domain Models (Week 1)

Start with pure domain logic that has no external dependencies. These are the easiest to test and form the foundation.

- WBSElement model — hierarchy, code generation, budget rollup

- Activity model — duration, constraints, validation

- Dependency model — types (FS, SS, FF, SF), lag validation

- Resource model — capacity, rates, calendar

Rationale: Domain models are pure Python classes with no I/O. They're fast to test, easy to refactor, and establish the vocabulary for the entire system.

## 2.2 Phase 2: CPM Engine (Week 1-2)

The scheduling engine is the mathematical core. Test against known reference schedules.

- Graph builder — construct DAG from activities/dependencies

- Topological sort — detect cycles, establish order

- Forward pass — ES/EF calculation for all dependency types

- Backward pass — LS/LF calculation

- Float calculation — total float, free float

- Critical path identification

- Constraint application (SNET, FNLT, etc.)

Rationale: CPM is deterministic and well-documented. Each step can be verified mathematically. Start with FS-only, then add other dependency types incrementally.

## 2.3 Phase 3: EVMS Calculator (Week 2-3)

EVMS metrics are arithmetic transformations of schedule and cost data.

- BCWS calculation — time-phased planned value

- BCWP calculation — all EV methods (0/100, 50/50, %, milestone)

- Variance calculations — SV, CV

- Index calculations — SPI, CPI

- Forecasting — EAC, ETC, VAC, TCPI

- Rollup aggregation — WBS hierarchy summation

Rationale: EVMS formulas are standardized per ANSI/EIA-748. Tests serve as executable documentation of the calculations.

## 2.4 Phase 4: Repository Layer (Week 3-4)

Data access with real database integration tests.

- WBSRepository — CRUD, ltree queries

- ActivityRepository — CRUD, bulk operations

- DependencyRepository — CRUD, cycle detection support

- BaselineRepository — immutable snapshot storage

- AuditLogRepository — append-only logging

## 2.5 Phase 5: API Layer (Week 4-5)

HTTP endpoints built on tested domain and repository layers.

## 2.6 Phase 6: Frontend Components (Week 5-6)

React components with mocked API responses.

# 3. Red-Green-Refactor Cycles

Concrete examples of TDD cycles for critical components.

## 3.1 Cycle: Forward Pass Calculation

RED — Write Failing Test First

# tests/unit/test_cpm_engine.py

import pytest

from datetime import date

from schedule_manager.cpm import CPMEngine

from schedule_manager.models import Activity, Dependency, DependencyType

class TestForwardPass:

def test_forward_pass_simple_chain(self):

'''A(5d) -> B(3d) -> C(2d) should give ES/EF: 0/5, 5/8, 8/10'''

# Arrange

activities = [

Activity(id=1, name='A', duration=5),

Activity(id=2, name='B', duration=3),

Activity(id=3, name='C', duration=2),

]

dependencies = [

Dependency(predecessor_id=1, successor_id=2, type=DependencyType.FS),

Dependency(predecessor_id=2, successor_id=3, type=DependencyType.FS),

]

engine = CPMEngine(activities, dependencies)

# Act

result = engine.forward_pass()

# Assert

assert result[1].early_start == 0

assert result[1].early_finish == 5

assert result[2].early_start == 5

assert result[2].early_finish == 8

assert result[3].early_start == 8

assert result[3].early_finish == 10

Run test: pytest tests/unit/test_cpm_engine.py::TestForwardPass -v

Expected result: FAILED (CPMEngine doesn't exist yet)

GREEN — Minimal Implementation

# schedule_manager/cpm.py

from dataclasses import dataclass

from typing import Dict, List

import networkx as nx

@dataclass

class ScheduleResult:

early_start: int

early_finish: int

late_start: int = None

late_finish: int = None

class CPMEngine:

def __init__(self, activities: List, dependencies: List):

self.activities = {a.id: a for a in activities}

self.dependencies = dependencies

self._build_graph()

def _build_graph(self):

self.graph = nx.DiGraph()

for a in self.activities.values():

self.graph.add_node(a.id, duration=a.duration)

for d in self.dependencies:

self.graph.add_edge(d.predecessor_id, d.successor_id,

type=d.type, lag=getattr(d, 'lag', 0))

def forward_pass(self) -> Dict[int, ScheduleResult]:

results = {}

for node in nx.topological_sort(self.graph):

predecessors = list(self.graph.predecessors(node))

if not predecessors:

es = 0

else:

es = max(results[p].early_finish for p in predecessors)

duration = self.graph.nodes[node]['duration']

results[node] = ScheduleResult(early_start=es, early_finish=es + duration)

return results

Run test: pytest tests/unit/test_cpm_engine.py::TestForwardPass -v

Expected result: PASSED

REFACTOR — Improve Without Changing Behavior

Refactoring opportunities after green:

- Extract _calculate_early_start() method for readability

- Add type hints for better IDE support

- Handle dependency types (currently assumes FS only)

- Add docstrings explaining the algorithm

After each refactor, re-run tests to ensure behavior is unchanged.

## 3.2 Cycle: SPI Calculation with Edge Cases

RED — Test Including Edge Case

# tests/unit/test_evms.py

import pytest

from decimal import Decimal

from evms.calculator import EVMSCalculator

class TestSPICalculation:

def test_spi_normal_case(self):

'''SPI = BCWP / BCWS'''

calc = EVMSCalculator(bcws=50000, bcwp=40000, acwp=45000)

assert calc.spi() == Decimal('0.80')

def test_spi_perfect_performance(self):

calc = EVMSCalculator(bcws=50000, bcwp=50000, acwp=50000)

assert calc.spi() == Decimal('1.00')

def test_spi_ahead_of_schedule(self):

calc = EVMSCalculator(bcws=50000, bcwp=60000, acwp=55000)

assert calc.spi() == Decimal('1.20')

def test_spi_division_by_zero(self):

'''When BCWS=0, SPI should be None (not calculable)'''

calc = EVMSCalculator(bcws=0, bcwp=0, acwp=0)

assert calc.spi() is None

def test_spi_rounding(self):

'''SPI should round to 2 decimal places'''

calc = EVMSCalculator(bcws=30000, bcwp=10000, acwp=15000)

assert calc.spi() == Decimal('0.33')  # 0.333... rounds to 0.33

GREEN — Implementation with Edge Case Handling

# evms/calculator.py

from decimal import Decimal, ROUND_HALF_UP

from typing import Optional

class EVMSCalculator:

def __init__(self, bcws: float, bcwp: float, acwp: float, bac: float = None):

self.bcws = Decimal(str(bcws))

self.bcwp = Decimal(str(bcwp))

self.acwp = Decimal(str(acwp))

self.bac = Decimal(str(bac)) if bac else None

def spi(self) -> Optional[Decimal]:

'''Schedule Performance Index = BCWP / BCWS'''

if self.bcws == 0:

return None

result = self.bcwp / self.bcws

return result.quantize(Decimal('0.01'), rounding=ROUND_HALF_UP)

REFACTOR Notes

- Consider extracting _safe_divide() for reuse in CPI, TCPI

- Add @property decorator for cleaner access

- Document that None return indicates 'not calculable'

## 3.3 Cycle: Circular Dependency Detection

RED — Test for Error Case

# tests/unit/test_cpm_engine.py

class TestCircularDependency:

def test_circular_dependency_detected(self):

'''A -> B -> C -> A should raise CircularDependencyError'''

activities = [

Activity(id=1, name='A', duration=5),

Activity(id=2, name='B', duration=3),

Activity(id=3, name='C', duration=2),

]

dependencies = [

Dependency(predecessor_id=1, successor_id=2, type=DependencyType.FS),

Dependency(predecessor_id=2, successor_id=3, type=DependencyType.FS),

Dependency(predecessor_id=3, successor_id=1, type=DependencyType.FS),  # Cycle!

]

with pytest.raises(CircularDependencyError) as exc_info:

CPMEngine(activities, dependencies)

assert 'cycle' in str(exc_info.value).lower()

assert exc_info.value.cycle_path == [1, 2, 3, 1]

GREEN — Implementation

# schedule_manager/exceptions.py

class CircularDependencyError(Exception):

def __init__(self, message: str, cycle_path: List[int]):

super().__init__(message)

self.cycle_path = cycle_path

# schedule_manager/cpm.py (updated __init__)

def __init__(self, activities: List, dependencies: List):

self.activities = {a.id: a for a in activities}

self.dependencies = dependencies

self._build_graph()

self._check_for_cycles()

def _check_for_cycles(self):

try:

cycle = nx.find_cycle(self.graph)

path = [edge[0] for edge in cycle] + [cycle[-1][1]]

raise CircularDependencyError(

f'Circular dependency detected: {" -> ".join(map(str, path))}',

cycle_path=path

)

except nx.NetworkXNoCycle:

pass  # No cycle found, graph is valid

# 4. Edge Cases & Error Handling Strategy

## 4.1 Error Handling Philosophy

The system uses a layered error handling approach:

| Layer | Error Type | Response |
| --- | --- | --- |
| Domain Model | ValidationError | Raise immediately, fail fast |
| CPM Engine | CircularDependencyError, ScheduleError | Raise with diagnostic info |
| Repository | IntegrityError, NotFoundError | Wrap DB errors, add context |
| API | HTTPException | Map to HTTP status codes |

## 4.2 Comprehensive Edge Case Tests

Schedule Boundary Conditions

class TestScheduleBoundaries:

def test_single_activity_schedule(self):

'''Schedule with only one activity'''

activities = [Activity(id=1, name='A', duration=5)]

engine = CPMEngine(activities, [])

result = engine.calculate()

assert result[1].early_start == 0

assert result[1].is_critical == True

def test_all_activities_parallel(self):

'''No dependencies - all start at 0'''

activities = [

Activity(id=1, name='A', duration=5),

Activity(id=2, name='B', duration=10),

Activity(id=3, name='C', duration=3),

]

engine = CPMEngine(activities, [])

result = engine.calculate()

for r in result.values():

assert r.early_start == 0

def test_extremely_long_schedule(self):

'''1000 sequential activities'''

activities = [Activity(id=i, name=f'A{i}', duration=1) for i in range(1000)]

dependencies = [

Dependency(predecessor_id=i, successor_id=i+1, type=DependencyType.FS)

for i in range(999)

]

import time

start = time.time()

engine = CPMEngine(activities, dependencies)

result = engine.calculate()

elapsed = time.time() - start

assert elapsed < 0.5  # Must complete in under 500ms

assert result[999].early_finish == 1000

# 5. Test Doubles Strategy

## 5.1 What to Mock vs. What to Use Real

| Component | Strategy | Rationale |
| --- | --- | --- |
| CPM Engine | REAL (no mocks) | Pure computation — fast, deterministic, mocking defeats the purpose |
| EVMS Calculator | REAL (no mocks) | Pure computation — tests ARE the specification |
| Database (unit tests) | MOCK | Isolate logic from I/O; use in-memory or mock repos |
| Database (integration) | REAL (test DB) | Test actual SQL, constraints, transactions |
| Redis Cache | MOCK or fakeredis | Avoid external dependency in unit tests |
| Jira API | MOCK | External service — use responses library or VCR.py |
| Cobra Integration | MOCK + fixtures | File-based — use sample files in test fixtures |
| Authentication | MOCK in unit, REAL in E2E | Unit tests bypass auth; E2E tests full flow |
| Background Tasks (Celery) | MOCK or EAGER mode | Use CELERY_TASK_ALWAYS_EAGER=True for sync testing |

## 5.2 Mock Implementation Examples

Repository Mock for Unit Tests

# tests/conftest.py

import pytest

from unittest.mock import MagicMock, AsyncMock

@pytest.fixture

def mock_activity_repo():

'''Mock repository for activity unit tests'''

repo = MagicMock()

repo.get_by_id = AsyncMock(return_value=Activity(

id=1, name='Test Activity', duration=5

))

repo.get_all_for_program = AsyncMock(return_value=[

Activity(id=1, name='A', duration=5),

Activity(id=2, name='B', duration=3),

])

repo.save = AsyncMock(return_value=None)

return repo

@pytest.fixture

def mock_dependency_repo():

repo = MagicMock()

repo.get_all_for_program = AsyncMock(return_value=[

Dependency(predecessor_id=1, successor_id=2, type=DependencyType.FS)

])

return repo

Real Test Database for Integration Tests

# tests/conftest.py

import pytest

from sqlalchemy.ext.asyncio import create_async_engine, AsyncSession

from sqlalchemy.orm import sessionmaker

@pytest.fixture(scope='session')

def test_engine():

'''Create test database engine'''

engine = create_async_engine(

'postgresql+asyncpg://test:test@localhost:5432/test_db',

echo=False

)

yield engine

engine.dispose()

@pytest.fixture

async def db_session(test_engine):

'''Create fresh session for each test, rollback after'''

async with test_engine.begin() as conn:

await conn.run_sync(Base.metadata.create_all)

async_session = sessionmaker(test_engine, class_=AsyncSession)

async with async_session() as session:

async with session.begin():

yield session

await session.rollback()

External API Mock (Jira)

# tests/conftest.py

import responses

@pytest.fixture

def mock_jira_api():

'''Mock Jira REST API responses'''

with responses.RequestsMock() as rsps:

rsps.add(

responses.GET,

'https://jira.example.com/rest/api/2/issue/PROJ-123',

json={

'key': 'PROJ-123',

'fields': {

'summary': 'Test Issue',

'status': {'name': 'In Progress'},

'customfield_10001': 100,  # Story points

}

},

status=200

)

yield rsps

## 5.3 Fixture Factory Pattern

Use Factory Boy for complex test data generation:

# tests/factories.py

import factory

from factory import fuzzy

class ProgramFactory(factory.Factory):

class Meta:

model = Program

id = factory.Sequence(lambda n: n + 1)

name = factory.Faker('company')

contract_number = factory.LazyAttribute(lambda _: f'W912HQ-24-C-{fuzzy.FuzzyInteger(1000, 9999).fuzz()}')

budget_at_completion = fuzzy.FuzzyDecimal(1000000, 100000000)

class WBSElementFactory(factory.Factory):

class Meta:

model = WBSElement

id = factory.Sequence(lambda n: n + 1)

name = factory.Faker('catch_phrase')

wbs_code = factory.Sequence(lambda n: f'1.{n}')

program = factory.SubFactory(ProgramFactory)

class ActivityFactory(factory.Factory):

class Meta:

model = Activity

id = factory.Sequence(lambda n: n + 1)

name = factory.Faker('bs')

duration = fuzzy.FuzzyInteger(1, 30)

wbs_element = factory.SubFactory(WBSElementFactory)

# Usage in tests:

def test_something():

activity = ActivityFactory(duration=10, name='Critical Task')

# Factory handles all other required fields

# 6. Test Coverage & CI Integration

## 6.1 Coverage Requirements

| Module | Target | Rationale |
| --- | --- | --- |
| schedule_manager/cpm.py | 90%+ | Core algorithm — correctness is critical |
| evms/calculator.py | 90%+ | Financial calculations — audit requirements |
| schedule_manager/models.py | 85%+ | Validation logic needs thorough testing |
| repositories/* | 80%+ | Data access — integration tests cover gaps |
| api/routes/* | 75%+ | E2E tests provide additional coverage |
| Overall | 80%+ | Balance thoroughness with development speed |

## 6.2 pytest Configuration

# pyproject.toml

[tool.pytest.ini_options]

minversion = '7.0'

testpaths = ['tests']

python_files = ['test_*.py']

python_functions = ['test_*']

asyncio_mode = 'auto'

addopts = '''

-v

--tb=short

--strict-markers

-ra

'''

markers = [

'unit: Unit tests (no external dependencies)',

'integration: Integration tests (requires database)',

'slow: Tests that take > 1 second',

'cpm: CPM engine tests',

'evms: EVMS calculation tests',

]

[tool.coverage.run]

source = ['schedule_manager', 'evms', 'api']

branch = true

omit = ['*/tests/*', '*/__pycache__/*']

[tool.coverage.report]

fail_under = 80

show_missing = true

exclude_lines = [

'pragma: no cover',

'raise NotImplementedError',

'if TYPE_CHECKING:',

]

## 6.3 GitHub Actions CI Pipeline

# .github/workflows/test.yml

name: Test Suite

on: [push, pull_request]

jobs:

unit-tests:

runs-on: ubuntu-latest

steps:

- uses: actions/checkout@v4

- uses: actions/setup-python@v5

with:

python-version: '3.11'

- run: pip install -e '.[test]'

- run: pytest tests/unit -m 'not slow' --cov --cov-report=xml

- uses: codecov/codecov-action@v3

integration-tests:

runs-on: ubuntu-latest

services:

postgres:

image: postgres:15

env:

POSTGRES_PASSWORD: test

options: --health-cmd pg_isready

steps:

- uses: actions/checkout@v4

- uses: actions/setup-python@v5

- run: pip install -e '.[test]'

- run: pytest tests/integration --cov --cov-append

cpm-validation:

runs-on: ubuntu-latest

steps:

- uses: actions/checkout@v4

- uses: actions/setup-python@v5

- run: pip install -e '.[test]'

- run: pytest tests/unit -m cpm -v --tb=long

# Appendix A: Reference Schedules for Validation

These reference schedules have known correct answers and should be used to validate CPM implementation.

## A.1 Simple Chain (Baseline)

A → B → C (all FS, no lag)

Durations: A=5, B=3, C=2

| Activity | ES | EF | LS | LF | TF |
| --- | --- | --- | --- | --- | --- |
| A | 0 | 5 | 0 | 5 | 0 |
| B | 5 | 8 | 5 | 8 | 0 |
| C | 8 | 10 | 8 | 10 | 0 |

Critical Path: A → B → C (all activities)

Project Duration: 10 days

## A.2 Parallel Paths

START → A → D → END

START → B → D → END

START → C → END

Durations: START=0, A=4, B=6, C=3, D=2, END=0

| Activity | ES | EF | LS | LF | TF |
| --- | --- | --- | --- | --- | --- |
| START | 0 | 0 | 0 | 0 | 0 |
| A | 0 | 4 | 2 | 6 | 2 |
| B | 0 | 6 | 0 | 6 | 0 |
| C | 0 | 3 | 5 | 8 | 5 |
| D | 6 | 8 | 6 | 8 | 0 |
| END | 8 | 8 | 8 | 8 | 0 |

Critical Path: START → B → D → END

Project Duration: 8 days

# Appendix B: EVMS Test Data Set

Reference data for validating EVMS calculations:

| WBS | BAC | BCWS | BCWP | ACWP | SPI | CPI |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 | 100,000 | 50,000 | 40,000 | 45,000 | 0.80 | 0.89 |
| 1.2 | 200,000 | 100,000 | 110,000 | 95,000 | 1.10 | 1.16 |
| 1.3 | 150,000 | 75,000 | 75,000 | 80,000 | 1.00 | 0.94 |
| TOTAL | 450,000 | 225,000 | 225,000 | 220,000 | 1.00 | 1.02 |

Derived metrics for validation: SV = $0, CV = $5,000, EAC = $441,176 (mathematical method)